## project
Design Stage
[6 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual | % Complete | Actual (beyond plan) | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Team Roles | 1 | 1 | 1 | 1 | 100%
Overview of Project | 1 | 1 | 1 | 1 | 100%
Intended IDE | 1 | 1 | 1 | 1 | 100%
Gantt Chart(s) | 1 | 1 | 1 | 1 | 100%
Risk Analysis | 1 | 1 | 1 | 1 | 100%
Management Approach | 1 | 1 | 1 | 1 | 100%
Details of Game/Demo | 2 | 2 | 2 | 1 | 100%
Evidence for Decision | 2 | 2 | 2 | 1 | 100%
Target Audience | 3 | 1 | 2 | 1 | 100%
Game Type | 3 | 1 | 2 | 1 | 100%
Game Platform | 3 | 1 | 2 | 1 | 100%
Gameplay Experience | 3 | 2 | 2 | 1 | 100%
Explain Graphics | 4 | 2 | 2 | 1 | 100%
Charatcer/Enviroment Sketches | 4 | 4 | 2 | 1 | 100%
Story | 4 | 1 | 2 | 1 | 100%
Level Design | 4 | 2 | 2 | 1 | 100%
Audio | 4 | 2 | 2 | 1 | 100%
Details of How Game Will Be Made | 5 | 3 | 2 | 1 | 100%
Development Process | 5 | 3 | 2 | 1 | 100%
Intended IDE(More Detail) | 6 | 1 | 2 | 1 | 100%
Target Enviroment | 6 | 2 | 2 | 1 | 100%
CreatePrototype | 3 | 5 | 3 | 5 | 100%
Presentation | 8 | 2 | 4 | 3 | 100%
Individual Evaluation | 10 | 1 | 10 | 1 | 100%
Blogs | 1 | 11 | 1 | 11 | 100%
Updated Plan | 9 | 2 | 9 | 1 | 100%
Evaluation | 10 | 1 | 10 | 1 | 100%